## Findings
ULUNDI MUNICIPALITY | [6 empty] | ACHIEVED = Remedial Action has been completed
ACTION PLAN ON A-G'S FINDINGS: 2019/2020 | [6 empty] | NOT ACHIEVED = Remedial Action not completed by the Implementation Date
ON-GOING/IN PROGRESS = No specific Implementation Date / Partially completed
No. | A-G Finding | Causal Factors | Remedial Action Plan | Responsible HoD | Implimentation Date | Management Reported Progress | Evidence (POE) Required | Status | Comments
1 | Going Concern: As disclosed in note 39 to the financial statements, the municipality's current liabilities exceeded its current assets by R120,24 million. Furthermore, Eskom debt is R121,76 million while cash on hand is only R6,02 million. These conditions indicate the existence of a material uncertainty that may cast significant doubt on the municipality's ability to continue as a going concern in the foreseeable future. | Eskom debt | To surrender/terminate the trading licence to Eskom where assets and liabilities will be set off. |  |  |  | Termination letter
|  |  | Honor repayment while the termination is still in progress |  |  |  | Proof of payment for the repayment
2 | Material losses - receivables from exchange transactions; AR 9: As disclosed in note 3.1.1 to the financial statements, the municipality recognised a provision for impairment of R8,07 million on receivables from exchange transactions as the recoverability of these amounts was doubtful. for impairment of R8,07 million on receivables from exchange transactions as the recoverability of these amounts was doubtful. | Socio economic factors | No action is to be taken as this not in control of the municipality but instead socio economic factors. This has been worsed by COVID 19. | Chief Financial Officer | Ongoing | The assessment will be done at the end of the year which will be based on the Provision for ba debts policy and also the balance oustnding as at that date.
3 | Material losses - electricity; AR 10: The municipality incurred material electricity losses of R22,49 m which represents 36% of total electricity purchased. | Inaccurate meter readings and illegal connections. | 1. Monthly Pre-billing checks. | Director, Technical | Monthly | Pre-billing for Jan done. Pre-billing for Feb done. | 1. Pre billing report.
|  |  | 2. Meter auditing and disconnections. | Director, Technical | Monthly | Meter audits: January = 836 February = 740 Disconnections: January = 140 February = 213 | 2. Audit and disconnection monthly report.
4 | Annual Financial Statements; AR27: The annual financial statements submitted for audit were not prepared in all material respects in accordance with the requirements of section 122 of the MFMA. Material misstatements on non-current assets, current assets, expenditure, disclosures and cash flow statement identified by the auditors in the submitted financial statements, were subsequently corrected, resulting in the financial statements receiving an unqualified audit opinion. |  | Refresher training by Provincial Treasury | Chief Financial Officer | 31/05/2021 | Request for a refresher training has been sent to treasury | Email and rsponse
2. Monthly Reconciliation of non current liabilities and commitments and cashflow statements.
5 | Expenditure Management: Money owed by the municipality was not always paid within 30 days, as required by section65(2)(e) of the MFMA. | This municipality has a challenge with Eskom debt which hinders timeous payments to other creditors such as Pension fund and SARS. | A 3-year Repayment Plan has been entered into with Eskom. |  |  |  | 1. New plan is attached as Eskom rejected the five year plan and opted for three years which is yet to be signed. Annexure E
|  |  | Continued implementation of the Financial Recovery Plan so that there is more expendable cash save for filling of critical positions. | Chief Financial Officer |  | The municipality strives to honor the Eskom invoices and repayment plan. | 2. Proof of payment to Eskom. Annexure F
|  |  | 3. Avoidance of payment of interest on late payments to other creditors. | MM | 2019-10-01 |  | 3. Proof of monthly cashflow management meetings.
|  |  | This will be resolved when termination of the licence has been finalised. |  |  | Termination process has been started
6 | Expenditure Management: Reasonable steps were not taken to prevent fruitless and wasteful expenditure amounting to R14,94 million, as disclosed in note 33.1 to the financial statements, in contravention of section 62(1)(d) of the MFMA. The majority of the expenditure was due to penalty interest incurred on late payment of accounts. | This municipality has a chalenge with Eskom debt which hinders timeous payments to other creditors such as Pension fund and SARS. | 1. A 3-year Repayment Plan has been entered into with Eskom |  |  | The municipality strives to honor the Eskom invoices and repayment plan. | 1. New plan is attached as Eskom rejected the five year plan and opted for three years which is yet to be signed. Annexure E
|  |  | This will be resolved when termination of the licence has been finalised. |  |  | Termination process has been started
|  |  | 2. Continued implementation of the Financial Recovery Plan so that there is more expendable cash save for filling of critical positions. |  |  |  | 2. Proof of payment to Eskom. Annexure F
|  |  | 3. Avoidance of payment of interest on late payments to other creditors. | MM |  |  | 3. Proof of monthly cashflow management meetings.
7 | Expenditure Management: Reasonable steps were not taken to prevent irregular expenditure amounting to R30,44 million as disclosed in note 33.2.1 to the financial statements, as required by section 62(1)(d) of the MFMA. The majority of the irregular expenditure was caused by the preference point system not being applied and bid documentation for the procurement of commodities designated for local content and production not stipulating minimum thresholds. | This was due to turnkey used in previous financial year. | 1. Appointment of contractors and Consultants seperately . Training of all bid committee members was done by Provincial Treasury wereby all members attended and training on local production content was done. | All HOD's | 31/3/2021 | In all current bids/tenders local production content is evaluated. List of appointed contractors | All bids awarded in 2020/21 financial year to comply as undertaken. There has been aapointments for contractors. Annexure J
8 | Consequence management; AR 31: Irregular as well as fruitless and wasteful expenditure incurred by the municipality was not investigated to determine if any person is liable for the expenditure, as required by Section 32(2) (b) of the MFMA. | UIFWE Committee with approved TOR did not exist. | UIFWE Committee to do investigations and report. | MM | Ongoing | UIFWE Committee to sit in March to consider what is in the Fruitless & Wasteful Expenditure vote since July 2019. | Investigation Report.
9 | Human resource management; AR 32: Appropriate systems and procedures to monitor, measure and evaluate performance of staff below the level of deputy director, were not developed and adopted, as required by s67 (1) (d) of the LG Systemes Act 2000. |  | 1. Establish a joint committee between Corporate & MM's Office to drive the process. | Director, Corporate | 2020-01-31 |  | 1. Notice of Meeting, Agenda and Attendance Registers.
|  |  | 2. Review PMS policy framework. | Director, Corporate | 2020-04-30 |  | Council Resolution
|  |  | 3. Develop Performance Agreements and Assessment Tools (for Levels below Section 54/56 Managers) | Director, Corporate | 2020-10-31 |  | Performance Agreement document & Assessment Tool.
|  |  | 4. Introduce PMS to the LLF. | Director, Corporate | 2020-05-31 |  | Notice of Meeting, Agenda, Minutes and Attendance Registers.
|  |  | 5. Workshop PMS to Extended Manco. | Director, Corporate | 2020-06-30 |  | Notice of Workshop, Attendance Register and Presentation.
|  |  | 6. Procure PMS system. | Director, Corporate | 2020-07-31 |  | Invoice & GRV.
|  |  | 7. Review Organisational Structure. | Director, Corporate | 2020-06-30 |  | Council resolution.
|  |  | 8. Adopt PMS policy. | Director, Corporate | 2020-06-30 |  | Council resolution
|  |  | 9. Implement PMS policy (to Levels below Section 54/56 Managers). | Director, Corporate | 2020-11-30 |  | Completed Performance agreements.
10 | Procurement and Contract Management; AR 33: Some of the goods and services with a transaction value of below R200 000 were procured without obtaining the required price quatations, in contravention of supply chain managment (SCM) regulation 17(a) and (c). Similiar non compliance was also reported in the prior year. | Non compliance with SCM regulations and SCM policy | To always obtain 3 quotations regarding transactions to the value below R200 000. | Chief Financial Officer | Ongoing | All procurement has been centralised. | Quotations. Annexure I
11 | Some of the quotations were accepted from bidders whose tax matters had not been declared by the South African Revenue Service to be in order, in contravention of SCM regulation 43 | Orders are issued while service providers are compliant while when later paying the status has chenged. | All payments be supported by CSD report | Chief Financial Officer | 31/3/2021 | Currently all payment related documentation is included in the payment voucher. | Confirmation of the status by Data capture through signature on the invoice.
13 | Senior management did not implement proper records management systems for the maintenance of documents supporting financial and performance information. This contributed to inaccurate reporting as evidenced by the quality of the financial statements and annual performance report. Management did not always adhere to legislative requirements pertaining to procurement and expenditure management due to a lack of consequences resulting from these transgressions | Document management | Voucher control certificate confirming all vouchers have been filed to be issued on monthly basis | Chief Financial Officer | 30/4/2020 | Voucher control certificate confirming all vouchers have been filed to be issued on monthly basis | Voucher certificates

## Sheet2
As disclosed in note 39 to the financial statements, the municipality's current liabilities exceeded its current assets by R120,24 million. Furthermore, Eskom debt is R121,76 million while cash on hand is only R6,02 million. These conditions indicate the existence of a material uncertainty that may cast significant doubt on the municipality's ability to continue as a going concern in the foreseeable future.

## Formula
Achieved
Not Achieved
Ongoing / In Progress
Not Due Yet